## Sheet1
Project_ID | Client_Name | Country | Industry | Lead_Source | Service_Interested | Budget | Project_Value | Currency | Start_Date | Deadline | Actual_Completion_Date | Project_Status | Assigned_Team_Size | Total_Hours_Logged | Overtime_Hours | Total Hours | Resource_Overallocated | Email | Contact_Number | Client_Satisfaction
P001 | Pixel Agency | UK | EdTech | Website | UI/UX Design | 8000 | 22000 | USD | 2026-01-03 | 2026-01-22 | 2026-01-29 | Completed | 7 | 139 | 20 | 159 | Yes | contact12@mail.com | 9014786744 | 1
P002 | AlphaTech | USA | SaaS | Website | Web Development | 5000 | 30000 | USD | 2026-01-10 | 2026-01-31 | 2026-02-02 | Completed | 2 | 176 | 5 | 181 | No | contact15@mail.com | Not Provided | 2
P003 | AlphaTech | USA | Healthcare | Google Ads | SEO | 12000 | 15000 | USD | 2026-01-11 | 2026-01-22 | 2026-01-22 | Completed | 3 | 305 | 10 | 315 | Yes | contact24@mail.com | 9849646938 | 4
P004 | Beta Solutions | UK | Fintech | LinkedIn | UI/UX Design | 12000 | 30000 | USD | 2026-01-25 | 2026-01-28 | 2026-02-04 | Completed | 3 | 172 | 0 | 172 | No | contact11@mail.com | 9320337646 | 4
P005 | Gamma Ltd | INDIA | Saas | Referral | SEO | 12000 | 9000 | USD | 2026-01-13 | 2026-01-18 | 2026-01-25 | Completed | 3 | 281 | 40 | 321 | Yes | contact27@mail.com | 9539133396 | 5
P006 | AlphaTech | UK | EdTech | Website | SEO | 15000 | 30000 | USD | 2026-01-05 | 2026-01-09 | 2026-01-16 | Completed | 8 | 120 | 60 | 180 | No | contact38@mail.com | Not Provided | 3
P007 | AlphaTech | USA | SaaS | Referral | UI/UX Design | 12000 | 25000 | USD | 2026-01-07 | 2026-01-09 | 2026-01-16 | Completed | 4 | 242 | 20 | 262 | No | contact44@mail.com | 9572551124 | 5
P008 | Pixel Agency | INDIA | SaaS | Website | UI/UX Design | 15000 | 12000 | USD | 2026-01-20 | 2026-02-04 | 2026-02-11 | Completed | 8 | 612 | 20 | 632 | Yes | contact16@mail.com | 9919707095 | 2
P009 | Beta Solutions | UK | EdTech | Website | SEO | 20000 | 15000 | USD | 2026-01-12 | 2026-01-20 | 2026-01-22 | Completed | 6 | 417 | 60 | 477 | No | contact30@mail.com | 9153092820 | 4
P010 | Vertex Global | CANADA | E-commerce | Referral | App Development | 5000 | 30000 | USD | 2026-01-13 | 2026-01-23 | 2026-01-30 | Completed | 5 | 615 | 20 | 635 | Yes | contact18@mail.com | 9869666139 | 3
P011 | AlphaTech | INDIA | FinTech | Website | Web Development | 12000 | 30000 | USD | 2026-01-23 | 2026-02-03 | 2026-02-24 | Delayed | 6 | 620 | 40 | 660 | Yes | contact50@mail.com | 9085117938 | 2
P012 | Delta Corp | UK | E-commerce | Website | UI/UX Design | 12000 | 15000 | USD | 2026-01-08 | 2026-01-13 | 2026-01-18 | Completed | 5 | 742 | 20 | 762 | Yes | contact1@mail.com | 9436498483 | 4
P013 | Vertex Global | CANADA | EdTech | Referral | UI/UX Design | 8000 | 12000 | USD | 2026-01-28 | 2026-03-03 | 2026-03-20 | In Progress | 8 | 495 | 20 | 515 | No | contact51@mail.com | 9915526035 | 3
P014 | Gamma Ltd | INDIA | Healthcare | Google Ads | UI/UX Design | 15000 | 22000 | USD | 2026-01-21 | 2026-01-21 | 2026-01-31 | Completed | 4 | 392 | 60 | 452 | No | contact31@mail.com | 9390725554 | 3
P015 | Nova Systems | INDIA | Healthcare | Website | SEO | 20000 | 12000 | USD | 2026-01-29 | 2026-03-10 | 2026-03-13 | In Progress | 5 | 684 | 10 | 694 | Yes | contact8@mail.com | 9936787285 | 3
P016 | Vertex Global | CANADA | EdTech | Google Ads | UI/UX Design | 5000 | 9000 | USD | 2026-01-16 | 2026-03-10 | 2026-03-17 | In Progress | 2 | 597 | 5 | 602 | No | contact59@mail.com | 9612526117 | 1
P017 | Gamma Ltd | UK | EdTech | Referral | App Development | 12000 | 22000 | USD | 2026-01-26 | 2026-03-09 | 2026-03-10 | In Progress | 7 | 313 | 60 | 373 | No | contact34@mail.com | 9610134610 | 4
P018 | Quantum Labs | USA | E-commerce | Referral | UI/UX Design | 15000 | 18000 | USD | 2026-01-03 | 2026-01-10 | 2026-01-17 | Completed | 8 | 879 | 10 | 889 | No | contact3@gmail.com | 9183669178 | 2
P019 | Delta Corp | CANADA | EdTech | Referral | App Development | 8000 | 18000 | USD | 2026-01-20 | 2026-02-04 | 2026-02-25 | Delayed | 8 | 787 | 20 | 807 | Yes | contact4@mail.com | 9456542803 | 5
P020 | Beta Solutions | UK | FinTech | LinkedIn | App Development | 12000 | 25000 | USD | 2026-01-23 | 2026-03-02 | 2026-03-02 | In Progress | 7 | 645 | 5 | 650 | Yes | contact33@mail.com | 9636876343 | 2
P021 | Nova Systems | AUSTRALIA | Healthcare | Google Ads | Web Development | 15000 | 18000 | USD | 2026-01-27 | 2026-01-29 | 2026-01-31 | Completed | 6 | 399 | 60 | 459 | No | contact13@mail.com | 9734659018 | 2
P022 | Quantum Labs | CANADA | SaaS | Website | UI/UX Design | 8000 | 12000 | USD | 2026-01-26 | 2026-03-23 | 2026-03-28 | In Progress | 3 | 879 | 0 | 879 | No | contact7@mail.com | 9753917547 | 1
P023 | Quantum Labs | CANADA | E-commerce | Referral | UI/UX Design | 20000 | 22000 | USD | 2026-01-06 | 2026-01-18 | 2026-01-21 | Completed | 8 | 593 | 10 | 603 | Yes | contact26@mail.com | Not Provided | 3
P024 | Omicron Tech | USA | Healthcare | Website | SEO | 15000 | 9000 | USD | 2026-01-07 | 2026-02-10 | 2026-02-11 | Completed | 6 | 312 | 10 | 322 | Yes | contact9@mail.com | 9891600041 | 2
P025 | Vertex Global | CANADA | SaaS | Referral | App Development | 12000 | 18000 | USD | 2026-01-10 | 2026-01-19 | 2026-01-23 | Completed | 6 | 418 | 60 | 478 | Yes | contact67@mail.com | 9402543787 | 4
P026 | Quantum Labs | CANADA | E-commerce | LinkedIn | App Development | 12000 | 12000 | USD | 2026-01-28 | 2026-02-21 | 2026-02-25 | Delayed | 8 | 283 | 0 | 283 | Yes | contact36@mail.com | 9428880171 | 4
P027 | Delta Corp | USA | EdTech | Referral | App Development | 12000 | 22000 | USD | 2026-01-25 | 2026-02-11 | 2026-02-18 | Completed | 4 | 534 | 10 | 544 | No | contact5@mail.com | 9638137771 | 4
P028 | Delta Corp | AUSTRALIA | EdTech | Google Ads | UI/UX Design | 8000 | 22000 | USD | 2026-01-18 | 2026-02-13 | 2026-02-16 | Completed | 6 | 404 | 10 | 414 | No | contact6@mail.com | 9045723578 | 3
P029 | Beta Solutions | CANADA | FinTech | LinkedIn | UI/UX Design | 20000 | 18000 | USD | 2026-01-31 | 2026-03-28 | 2026-03-29 | In Progress | 8 | 874 | 5 | 879 | Yes | contact39@mail.com | 9957659403 | 2
P030 | Quantum Labs | CANADA | EdTech | Referral | Web Development | 15000 | 12000 | USD | 2026-01-04 | 2026-02-26 | 2026-02-27 | In Progress | 7 | 465 | 0 | 465 | Yes | contact40@mail.com | 9770797830 | 2
P031 | Beta Solutions | CANADA | Fintech | Website | UI/UX Design | 15000 | 30000 | USD | 2026-01-19 | 2026-02-27 | 2026-03-06 | In Progress | 3 | 714 | 0 | 714 | No | contact56@mail.com | 9192782196 | 1
P032 | Quantum Labs | UK | E-commerce | LinkedIn | Web Development | 20000 | 15000 | USD | 2026-01-22 | 2026-02-14 | 2026-02-21 | Delayed | 6 | 542 | 40 | 582 | No | contact49@mail.com | Not Provided | 1
P033 | Delta Corp | CANADA | FinTech | LinkedIn | SEO | 5000 | 9000 | USD | 2026-01-22 | 2026-03-17 | 2026-03-24 | In Progress | 6 | 336 | 60 | 396 | No | contact20@mail.com | 9395111138 | 5
P034 | Gamma Ltd | USA | FinTech | Referral | App Development | 20000 | 12000 | USD | 2026-01-05 | 2026-01-05 | 2026-01-06 | Completed | 8 | 606 | 60 | 666 | No | contact41@mail.com | 9507886467 | 1
P035 | Beta Solutions | CANADA | EdTech | LinkedIn | App Development | 5000 | 15000 | USD | 2026-01-09 | 2026-02-20 | 2026-02-27 | Delayed | 5 | 537 | 40 | 577 | No | contact66@mail.com | 9944296105 | 3
P036 | Vertex Global | USA | FinTech | Google Ads | App Development | 20000 | 25000 | USD | 2026-01-04 | 2026-02-09 | 2026-02-16 | completed | 6 | 630 | 40 | 670 | No | contact74@mail.com | 9024540871 | 5
P037 | Omicron Tech | USA | SaaS | Website | UI/UX Design | 15000 | 9000 | USD | 2026-01-01 | 2026-01-18 | 2026-01-26 | Completed | 2 | 152 | 5 | 157 | Yes | contact10@mail.com | 9111019967 | 1
P038 | Quantum Labs | INDIA | E-commerce | Website | App Development | 12000 | 30000 | USD | 2026-01-25 | 2026-02-21 | 2026-02-28 | In Progress | 5 | 852 | 5 | 857 | Yes | contact52@mail.com | 9579779143 | 1
P039 | Beta Solutions | USA | FinTech | Website | SEO | 15000 | 30000 | USD | 2026-01-14 | 2026-01-18 | 2026-01-25 | Completed | 7 | 538 | 60 | 598 | Yes | contact81@mail.com | Not Provided | 4
P040 | AlphaTech | UK | E-commerce | Website | SEO | 20000 | 25000 | USD | 2026-01-31 | 2026-02-23 | 2026-03-02 | Delayed | 6 | 401 | 60 | 461 | Yes | contact57@mail.com | 9329998183 | 1
P041 | Gamma Ltd | CANADA | Fintech | Website | Web Development | 12000 | 22000 | USD | 2026-01-25 | 2026-02-18 | 2026-02-25 | Delayed | 4 | 665 | 10 | 675 | No | contact53@mail.com | 9033291469 | 2
P042 | ZetaSoft | USA | EdTech | LinkedIn | Web Development | 8000 | 30000 | USD | 2026-01-26 | 2026-03-25 | 2026-04-01 | In Progress | 2 | 764 | 20 | 784 | Yes | contact2@mail.com | 9745582386 | 4
P043 | Quantum Labs | AUSTRALIA | E-commerce | Referral | Web Development | 5000 | 9000 | USD | 2026-01-21 | 2026-01-27 | 2026-02-03 | Completed | 6 | 749 | 10 | 759 | No | contact60@mail.com | 9792953697 | 1
P044 | Gamma Ltd | USA | SaaS | Referral | SEO | 12000 | 12000 | USD | 2026-01-21 | 2026-02-10 | 2026-02-13 | Completed | 5 | 560 | 0 | 560 | Yes | contact54@mail.com | Not Provided | 1
P045 | Quantum Labs | USA | E-commerce | LinkedIn | UI/UX Design | 5000 | 22000 | USD | 2026-01-05 | 2026-02-06 | 2026-02-10 | Completed | 4 | 511 | 40 | 551 | Yes | contact65@mail.com | 9491762343 | 5
P046 | Omicron Tech | AUSTRALIA | Healthcare | LinkedIn | App Development | 8000 | 9000 | USD | 2026-01-20 | 2026-01-29 | 2026-01-30 | Completed | 8 | 429 | 60 | 489 | No | contact22@mail.com | 9678017919 | 4
P047 | ZetaSoft | USA | EdTech | Referral | UI/UX Design | 20000 | 22000 | USD | 2026-01-04 | 2026-02-04 | 2026-02-09 | Completed | 7 | 848 | 10 | 858 | No | contact14@mail.com | 9429662058 | 4
P048 | ZetaSoft | INDIA | FinTech | Website | App Development | 8000 | 18000 | USD | 2026-01-18 | 2026-03-19 | 2026-03-20 | In Progress | 6 | 863 | 10 | 873 | No | contact17@mail.com | 9892483107 | 3
P049 | ZetaSoft | INDIA | SaaS | Google Ads | UI/UX Design | 12000 | 12000 | USD | 2026-01-19 | 2026-01-19 | 2026-01-27 | Completed | 4 | 728 | 10 | 738 | Yes | contact19@mail.com | 9217345450 | 2
P050 | ZetaSoft | UK | Healthcare | Referral | Web Development | 12000 | 12000 | USD | 2026-01-21 | 2026-02-28 | 2026-03-04 | In Progress | 4 | 562 | 10 | 572 | Yes | contact21@mail.com | 9331475503 | 2
P051 | Nova Systems | UK | Healthcare | LinkedIn | UI/UX Design | 8000 | 12000 | USD | 2026-01-19 | 2026-01-22 | 2026-01-28 | Completed | 2 | 759 | 0 | 759 | No | contact23@mail.com | 9969108135 | 3
P052 | Beta Solutions | INDIA | E-commerce | Referral | App Development | 12000 | 9000 | USD | 2026-01-28 | 2026-02-11 | 2026-02-18 | Delayed | 3 | 750 | 5 | 755 | No | contact100@mail.com | 9952412041 | 1
P053 | Delta Corp | UK | FinTech | Website | Web Development | 15000 | 30000 | USD | 2026-01-30 | 2026-03-07 | 2026-03-21 | In Progress | 7 | 271 | 60 | 331 | No | contact25@mail.com | 9283970406 | 5
P054 | Beta Solutions | UK | EdTech | Google Ads | SEO | 20000 | 30000 | USD | 2026-01-28 | 2026-02-03 | 2026-02-28 | Delayed | 3 | 506 | 0 | 506 | No | contact107@mail.com | 9623427591 | 4
P055 | ZetaSoft | UK | E-commerce | Google Ads | SEO | 12000 | 12000 | USD | 2026-01-16 | 2026-02-27 | 2026-03-03 | In Progress | 6 | 368 | 5 | 373 | Yes | contact32@mail.com | 9841407346 | 5
P056 | AlphaTech | USA | Healthcare | Google Ads | Web Development | 8000 | 22000 | USD | 2026-01-11 | 2026-02-07 | 2026-02-28 | In Progress | 5 | 514 | 20 | 534 | No | contact75@mail.com | Not Provided | 2
P057 | Omicron Tech | AUSTRALIA | Healthcare | LinkedIn | UI/UX Design | 12000 | 30000 | USD | 2026-01-21 | 2026-02-06 | 2026-02-15 | Completed | 4 | 817 | 40 | 857 | No | contact47@mail.com | 9069582738 | 3
P058 | Omicron Tech | AUSTRALIA | SaaS | Google Ads | App Development | 8000 | 30000 | USD | 2026-01-06 | 2026-01-07 | 2026-01-12 | Completed | 7 | 317 | 0 | 317 | No | contact58@mail.com | Not Provided | 3
P059 | Beta Solutions | USA | EdTech | Google Ads | UI/UX Design | 8000 | 18000 | USD | 2026-01-09 | 2026-01-09 | 2026-01-16 | Completed | 2 | 234 | 20 | 254 | Yes | contact109@mail.com | 9007661873 | 4
P060 | Vertex Global | INDIA | EdTech | Website | SEO | 12000 | 12000 | USD | 2026-01-24 | 2026-02-27 | 2026-03-06 | In Progress | 4 | 230 | 60 | 290 | No | contact77@mail.com | 9672933768 | 5
P061 | Delta Corp | UK | EdTech | Google Ads | UI/UX Design | 15000 | 30000 | USD | 2026-01-20 | 2026-03-07 | 2026-03-28 | In Progress | 6 | 387 | 5 | 392 | Yes | contact29@mail.com | 9872781954 | 1
P062 | Pixel Agency | USA | SaaS | Google Ads | App Development | 12000 | 18000 | USD | 2026-01-09 | 2026-01-27 | 2026-02-03 | Completed | 2 | 337 | 40 | 377 | Yes | contact48@mail.com | 9907654409 | 2
P063 | ZetaSoft | CANADA | E-commerce | Google Ads | UI/UX Design | 12000 | 12000 | USD | 2026-01-31 | 2026-03-07 | 2026-03-12 | In Progress | 2 | 820 | 0 | 820 | No | contact37@mail.com | 9438093540 | 2
P064 | Beta Solutions | INDIA | E-commerce | LinkedIn | UI/UX Design | 15000 | 12000 | USD | 2026-01-24 | 2026-01-30 | 2026-01-31 | Completed | 8 | 283 | 0 | 283 | No | contact117@mail.com | 9574009637 | 2
P065 | ZetaSoft | UK | Healthcare | Website | App Development | 5000 | 22000 | USD | 2026-01-23 | 2026-02-25 | 2026-02-27 | In Progress | 6 | 893 | 20 | 913 | No | contact43@mail.com | 9826361212 | 2
P066 | AlphaTech | INDIA | E-commerce | Referral | UI/UX Design | 12000 | 12000 | USD | 2026-01-11 | 2026-02-16 | 2026-02-23 | Delayed | 8 | 244 | 60 | 304 | Yes | contact84@mail.com | 9960202598 | 2
P067 | Pixel Agency | AUSTRALIA | SaaS | LinkedIn | SEO | 15000 | 25000 | USD | 2026-01-31 | 2026-02-24 | 2026-02-28 | In Progress | 2 | 877 | 20 | 897 | Yes | contact61@mail.com | 9955523852 | 2
P068 | AlphaTech | INDIA | E-commerce | Referral | App Development | 15000 | 12000 | USD | 2026-01-01 | 2026-02-21 | 2026-02-28 | In Progress | 5 | 206 | 10 | 216 | No | contact85@mail.com | 9424598523 | 2
P069 | Vertex Global | AUSTRALIA | EdTech | LinkedIn | SEO | 12000 | 15000 | USD | 2026-01-24 | 2026-01-26 | 2026-01-30 | Completed | 3 | 724 | 5 | 729 | No | contact87@mail.com | 9116802380 | 5
P070 | Nova Systems | AUSTRALIA | E-commerce | Website | App Development | 12000 | 18000 | USD | 2026-01-06 | 2026-01-28 | 2026-02-04 | Completed | 8 | 414 | 60 | 474 | No | contact28@mail.com | 9793236188 | 4
P071 | ZetaSoft | AUSTRALIA | FinTech | LinkedIn | UI/UX Design | 5000 | 9000 | USD | 2026-01-01 | 2026-02-10 | 2026-02-12 | Delayed | 5 | 767 | 40 | 807 | Yes | contact45@mail.com | 9236286038 | 3
P072 | Vertex Global | CANADA | SaaS | Google Ads | Web Development | 20000 | 25000 | USD | 2026-01-25 | 2026-03-11 | 2026-03-15 | In Progress | 4 | 554 | 0 | 554 | No | contact92@mail.com | 9942037835 | 3
P073 | Delta Corp | INDIA | SaaS | LinkedIn | SEO | 5000 | 12000 | USD | 2026-01-05 | 2026-01-17 | 2026-01-24 | Completed | 7 | 539 | 10 | 549 | Yes | contact35@mail.com | 9726753134 | 4
P074 | Pixel Agency | CANADA | FinTech | Google Ads | SEO | 15000 | 9000 | USD | 2026-01-18 | 2026-01-22 | 2026-01-27 | Completed | 5 | 628 | 20 | 648 | Yes | contact68@mail.com | 9289821192 | 5
P075 | Nova Systems | UK | EdTech | Referral | SEO | 20000 | 15000 | USD | 2026-01-18 | 2026-01-28 | 2026-01-29 | Completed | 5 | 246 | 10 | 256 | No | contact42@mail.com | Not Provided | 5
P076 | Quantum Labs | CANADA | Healthcare | Referral | App Development | 15000 | 15000 | USD | 2026-01-28 | 2026-03-02 | 2026-03-07 | In Progress | 3 | 869 | 5 | 874 | Yes | contact76@mail.com | 9809023121 | 3
P077 | Vertex Global | USA | SaaS | Google Ads | App Development | 15000 | 30000 | USD | 2026-01-08 | 2026-03-09 | 2026-03-19 | In Progress | 4 | 484 | 10 | 494 | Yes | contact118@mail.com | 9137480340 | 3
P078 | Nova Systems | INDIA | Healthcare | Referral | Web Development | 15000 | 30000 | USD | 2026-01-20 | 2026-02-06 | 2026-02-13 | Completed | 6 | 840 | 10 | 850 | Yes | contact55@mail.com | 9339305772 | 3
P079 | Quantum Labs | UK | SaaS | Referral | Web Development | 12000 | 18000 | USD | 2026-01-26 | 2026-02-10 | 2026-02-17 | Completed | 3 | 675 | 20 | 695 | No | contact83@mail.com | 9656449892 | 2
P080 | Beta Solutions | INDIA | E-commerce | Referral | App Development | 5000 | 15000 | USD | 2026-01-19 | 2026-03-03 | 2026-03-21 | In Progress | 6 | 188 | 5 | 193 | Yes | contact126@mail.com | 9979217189 | 4
P081 | AlphaTech | CANADA | SaaS | Website | App Development | 8000 | 25000 | USD | 2026-01-24 | 2026-03-25 | 2026-03-29 | In Progress | 8 | 275 | 0 | 275 | Yes | contact88@mail.com | 9699375743 | 5
P082 | Beta Solutions | CANADA | FinTech | LinkedIn | SEO | 20000 | 30000 | USD | 2026-01-25 | 2026-02-24 | 2026-03-03 | Delayed | 2 | 209 | 0 | 209 | No | contact128@mail.com | 9269249727 | 5
P083 | Gamma Ltd | USA | E-commerce | LinkedIn | UI/UX Design | 12000 | 22000 | USD | 2026-01-05 | 2026-01-19 | 2026-01-26 | Completed | 2 | 815 | 5 | 820 | Yes | contact62@mail.com | 9714484542 | 4
P084 | AlphaTech | USA | Healthcare | Referral | UI/UX Design | 12000 | 22000 | USD | 2026-01-26 | 2026-03-19 | 2026-03-22 | In Progress | 8 | 738 | 10 | 748 | No | contact115@mail.com | 9243364043 | 1
P085 | Vertex Global | USA | SaaS | Google Ads | SEO | 12000 | 18000 | USD | 2026-01-24 | 2026-01-24 | 2026-01-31 | Completed | 6 | 480 | 40 | 520 | Yes | contact122@mail.com | 9944134209 | 2
P086 | Vertex Global | USA | FinTech | LinkedIn | Web Development | 12000 | 18000 | USD | 2026-01-24 | 2026-01-26 | 2026-02-02 | Completed | 7 | 476 | 40 | 516 | No | contact142@mail.com | 9429465248 | 4
P087 | Omicron Tech | UK | EdTech | LinkedIn | App Development | 12000 | 12000 | USD | 2026-01-24 | 2026-03-24 | 2026-03-28 | In Progress | 6 | 370 | 10 | 380 | Yes | contact103@mail.com | 9607677119 | 4
P088 | Quantum Labs | UK | Healthcare | Website | Web Development | 8000 | 25000 | USD | 2026-01-06 | 2026-01-06 | 2026-01-13 | Completed | 4 | 687 | 60 | 747 | Yes | contact86@mail.com | 9423763263 | 2
P089 | Quantum Labs | CANADA | Healthcare | Referral | Web Development | 15000 | 12000 | USD | 2026-01-15 | 2026-01-17 | 2026-01-20 | Completed | 3 | 123 | 20 | 143 | No | contact98@mail.com | 9201554480 | 4
P090 | Nova Systems | UK | Healthcare | Referral | Web Development | 12000 | 15000 | USD | 2026-01-26 | 2026-01-26 | 2026-01-31 | Completed | 5 | 859 | 40 | 899 | Yes | contact63@mail.com | 9600537855 | 1
P091 | Omicron Tech | UK | EdTech | Google Ads | App Development | 12000 | 30000 | USD | 2026-01-21 | 2026-02-04 | 2026-02-14 | Completed | 5 | 408 | 0 | 408 | No | contact111@mail.com | Not Provided | 1
P092 | Vertex Global | USA | FinTech | Referral | App Development | 5000 | 30000 | USD | 2026-01-28 | 2026-03-22 | 2026-03-24 | In Progress | 8 | 559 | 60 | 619 | Yes | contact164@mail.com | Not Provided | 4
P093 | Omicron Tech | UK | EdTech | Website | Web Development | 12000 | 30000 | USD | 2026-01-18 | 2026-01-18 | 2026-01-27 | Completed | 5 | 418 | 40 | 458 | No | contact112@mail.com | 9464335720 | 3
P094 | Beta Solutions | UK | EdTech | Google Ads | SEO | 15000 | 22000 | USD | 2026-01-03 | 2026-02-14 | 2026-02-14 | Completed | 8 | 799 | 60 | 859 | Yes | contact143@mail.com | 9694050404 | 1
P095 | Beta Solutions | INDIA | E-commerce | LinkedIn | App Development | 5000 | 15000 | USD | 2026-01-05 | 2026-01-10 | 2026-01-15 | Completed | 5 | 548 | 10 | 558 | Yes | contact145@mail.com | 9489115633 | 2
P096 | Quantum Labs | UK | SaaS | LinkedIn | UI/UX Design | 20000 | 18000 | USD | 2026-01-12 | 2026-02-20 | 2026-02-27 | Delayed | 2 | 501 | 40 | 541 | Yes | contact99@mail.com | 9045275382 | 2
P097 | Omicron Tech | USA | Healthcare | Website | SEO | 15000 | 22000 | USD | 2026-01-21 | 2026-03-22 | 2026-03-28 | In Progress | 2 | 745 | 60 | 805 | Yes | contact114@mail.com | 9946871215 | 4
P098 | Delta Corp | USA | E-commerce | Website | SEO | 5000 | 22000 | USD | 2026-01-16 | 2026-01-21 | 2026-01-25 | Completed | 3 | 728 | 10 | 738 | Yes | contact70@mail.com | 9874033472 | 4
P099 | Quantum Labs | INDIA | SaaS | Website | UI/UX Design | 12000 | 25000 | USD | 2026-01-25 | 2026-01-27 | 2026-02-03 | Completed | 7 | 178 | 10 | 188 | No | contact105@mail.com | 9356056261 | 5
P100 | Delta Corp | USA | E-commerce | Referral | UI/UX Design | 12000 | 9000 | USD | 2026-01-03 | 2026-01-31 | 2026-01-31 | Completed | 6 | 385 | 40 | 425 | Yes | contact80@mail.com | 9263468812 | 5
P101 | Nova Systems | AUSTRALIA | EdTech | Google Ads | UI/UX Design | 8000 | 9000 | USD | 2026-01-16 | 2026-02-22 | 2026-02-22 | Delayed | 7 | 865 | 60 | 925 | No | contact64@mail.com | 9766973606 | 5
P102 | Quantum Labs | UK | Healthcare | Website | UI/UX Design | 8000 | 30000 | USD | 2026-01-05 | 2026-01-20 | 2026-01-24 | Completed | 6 | 690 | 60 | 750 | Yes | contact136@mail.com | 9372076174 | 3
P103 | ZetaSoft | USA | FinTech | Website | App Development | 12000 | 15000 | USD | 2026-01-07 | 2026-01-25 | 2026-01-30 | Completed | 4 | 145 | 60 | 205 | No | contact46@mail.com | 9608292051 | 5
P104 | Pixel Agency | USA | E-commerce | Google Ads | SEO | 5000 | 9000 | USD | 2026-01-04 | 2026-02-23 | 2026-02-27 | In Progress | 4 | 242 | 0 | 242 | Yes | contact69@mail.com | 9270422526 | 3
P105 | Quantum Labs | CANADA | SaaS | Referral | App Development | 20000 | 22000 | USD | 2026-01-28 | 2026-02-04 | 2026-02-14 | Completed | 7 | 597 | 5 | 602 | No | contact154@mail.com | Not Provided | 5
P106 | Pixel Agency | USA | Healthcare | LinkedIn | UI/UX Design | 12000 | 15000 | USD | 2026-01-01 | 2026-01-06 | 2026-01-15 | Completed | 7 | 274 | 40 | 314 | No | contact73@mail.com | 9839867141 | 1
P107 | Delta Corp | UK | FinTech | LinkedIn | SEO | 12000 | 22000 | USD | 2026-01-22 | 2026-03-10 | 2026-03-17 | In Progress | 7 | 426 | 5 | 431 | No | contact95@mail.com | 9243620821 | 5
P108 | Vertex Global | USA | FinTech | Google Ads | UI/UX Design | 8000 | 15000 | USD | 2026-01-09 | 2026-02-19 | 2026-02-26 | Delayed | 6 | 710 | 60 | 770 | No | contact165@mail.com | Not Provided | 2
P109 | Quantum Labs | CANADA | EdTech | LinkedIn | Web Development | 12000 | 15000 | USD | 2026-01-08 | 2026-02-26 | 2026-02-28 | In Progress | 8 | 258 | 5 | 263 | No | contact155@mail.com | Not Provided | 1
P110 | Delta Corp | CANADA | E-commerce | Website | SEO | 12000 | 12000 | USD | 2026-01-08 | 2026-02-03 | 2026-02-24 | Completed | 5 | 555 | 20 | 575 | No | contact101@mail.com | 9885939955 | 4
P111 | Omicron Tech | CANADA | E-commerce | LinkedIn | Web Development | 8000 | 22000 | USD | 2026-01-18 | 2026-02-03 | 2026-02-10 | Completed | 2 | 607 | 40 | 647 | No | contact130@mail.com | 9045797527 | 1
P112 | AlphaTech | INDIA | E-commerce | Referral | Web Development | 20000 | 9000 | USD | 2026-01-03 | 2026-01-04 | 2026-01-11 | Completed | 7 | 676 | 60 | 736 | Yes | contact121@mail.com | 9191920287 | 2
P113 | Pixel Agency | AUSTRALIA | FinTech | LinkedIn | UI/UX Design | 12000 | 15000 | USD | 2026-01-17 | 2026-02-08 | 2026-02-17 | Completed | 3 | 209 | 40 | 249 | Yes | contact79@mail.com | 9184391734 | 1
P114 | ZetaSoft | UK | EdTech | Website | SEO | 15000 | 18000 | USD | 2026-01-22 | 2026-02-01 | 2026-02-10 | Completed | 2 | 595 | 10 | 605 | Yes | contact72@mail.com | 9329567833 | 1
P115 | Delta Corp | UK | SaaS | LinkedIn | UI/UX Design | 8000 | 12000 | USD | 2026-01-05 | 2026-03-03 | 2026-03-03 | In Progress | 3 | 508 | 0 | 508 | Yes | contact108@mail.com | 9465702224 | 1
P116 | Quantum Labs | AUSTRALIA | Healthcare | Website | UI/UX Design | 15000 | 30000 | USD | 2026-01-28 | 2026-03-10 | 2026-03-15 | In Progress | 8 | 787 | 20 | 807 | Yes | contact156@mail.com | Not Provided | 2
P117 | Gamma Ltd | UK | EdTech | Website | App Development | 12000 | 25000 | USD | 2026-01-30 | 2026-03-03 | 2026-03-10 | In Progress | 4 | 687 | 5 | 692 | No | contact71@mail.com | 9871296767 | 4
P118 | Omicron Tech | INDIA | SaaS | LinkedIn | App Development | 5000 | 15000 | USD | 2026-01-27 | 2026-03-22 | 2026-03-29 | In Progress | 8 | 368 | 10 | 378 | No | contact131@mail.com | 9092397754 | 1
P119 | ZetaSoft | INDIA | FinTech | Referral | SEO | 15000 | 18000 | USD | 2026-01-22 | 2026-03-02 | 2026-03-26 | In Progress | 8 | 748 | 10 | 758 | No | contact102@mail.com | 9806393873 | 1
P120 | AlphaTech | UK | SaaS | Website | UI/UX Design | 20000 | 15000 | USD | 2026-01-01 | 2026-01-10 | 2026-01-17 | Completed | 7 | 134 | 40 | 174 | Yes | contact135@mail.com | 9835811702 | 2
P121 | Gamma Ltd | AUSTRALIA | FinTech | LinkedIn | SEO | 5000 | 15000 | USD | 2026-01-30 | 2026-03-24 | 2026-03-31 | In Progress | 5 | 480 | 5 | 485 | Yes | contact89@mail.com | 9098220978 | 2
P122 | Nova Systems | CANADA | E-commerce | Website | Web Development | 8000 | 18000 | USD | 2026-01-20 | 2026-01-21 | 2026-01-28 | Completed | 3 | 155 | 10 | 165 | Yes | contact78@mail.com | Not Provided | 1
P123 | Omicron Tech | INDIA | FinTech | Website | App Development | 5000 | 25000 | USD | 2026-01-03 | 2026-01-04 | 2026-01-11 | Completed | 8 | 698 | 40 | 738 | No | contact134@mail.com | 9308793669 | 1
P124 | Delta Corp | UK | Healthcare | Website | SEO | 15000 | 12000 | USD | 2026-01-20 | 2026-03-21 | 2026-03-28 | In Progress | 7 | 749 | 5 | 754 | Yes | contact110@mail.com | 9908337788 | 4
P125 | Nova Systems | CANADA | E-commerce | LinkedIn | Web Development | 12000 | 30000 | USD | 2026-01-17 | 2026-01-24 | 2026-01-24 | Completed | 2 | 569 | 0 | 569 | Yes | contact82@mail.com | 9665042396 | 1
P126 | Beta Solutions | AUSTRALIA | SaaS | Website | SEO | 8000 | 15000 | USD | 2026-01-04 | 2026-02-26 | 2026-02-28 | In Progress | 4 | 366 | 60 | 426 | Yes | contact146@mail.com | 9029035746 | 3
P127 | Omicron Tech | AUSTRALIA | Healthcare | Website | SEO | 5000 | 25000 | USD | 2026-01-13 | 2026-01-20 | 2026-01-27 | Completed | 6 | 680 | 10 | 690 | Yes | contact150@mail.com | 9882085530 | 3
P128 | Pixel Agency | AUSTRALIA | FinTech | Website | Web Development | 8000 | 18000 | USD | 2026-01-17 | 2026-01-23 | 2026-01-29 | Completed | 2 | 616 | 0 | 616 | No | contact90@mail.com | 9630035940 | 2
P129 | Beta Solutions | AUSTRALIA | SaaS | Website | SEO | 12000 | 22000 | USD | 2026-01-10 | 2026-01-22 | 2026-01-22 | Completed | 8 | 156 | 0 | 156 | Yes | contact159@mail.com | Not Provided | 1
P130 | Omicron Tech | USA | Healthcare | LinkedIn | Web Development | 8000 | 9000 | USD | 2026-01-17 | 2026-01-17 | 2026-01-24 | Completed | 4 | 710 | 60 | 770 | No | contact152@mail.com | Not Provided | 3
P131 | Omicron Tech | CANADA | SaaS | Website | SEO | 5000 | 9000 | USD | 2026-01-09 | 2026-01-19 | 2026-01-29 | Completed | 5 | 780 | 5 | 785 | Yes | contact153@mail.com | Not Provided | 3
P132 | Pixel Agency | UK | Healthcare | Referral | SEO | 20000 | 30000 | USD | 2026-01-25 | 2026-02-27 | 2026-03-04 | In Progress | 4 | 155 | 5 | 160 | No | contact96@mail.com | 9329951946 | 3
P133 | Quantum Labs | INDIA | SaaS | Referral | Web Development | 8000 | 12000 | USD | 2026-01-05 | 2026-03-01 | 2026-03-08 | In Progress | 3 | 857 | 60 | 917 | Yes | contact157@mail.com | Not Provided | 5
P134 | AlphaTech | USA | Healthcare | Website | App Development | 12000 | 18000 | USD | 2026-01-25 | 2026-02-05 | 2026-02-05 | Completed | 4 | 182 | 60 | 242 | Yes | contact140@mail.com | 9465156490 | 2
P135 | AlphaTech | UK | EdTech | Referral | UI/UX Design | 15000 | 25000 | USD | 2026-01-13 | 2026-03-04 | 2026-03-07 | In Progress | 8 | 201 | 20 | 221 | Yes | contact144@mail.com | Not Provided | 2
P136 | Delta Corp | INDIA | FinTech | Google Ads | UI/UX Design | 12000 | 15000 | USD | 2026-01-15 | 2026-02-11 | 2026-02-16 | Completed | 2 | 264 | 20 | 284 | Yes | contact113@mail.com | 9304809864 | 2
P137 | Gamma Ltd | UK | E-commerce | Website | UI/UX Design | 12000 | 12000 | USD | 2026-01-15 | 2026-01-26 | 2026-02-18 | Completed | 4 | 864 | 60 | 924 | Yes | contact91@mail.com | 9427359158 | 5
P138 | ZetaSoft | UK | FinTech | Website | SEO | 12000 | 15000 | USD | 2026-01-18 | 2026-02-14 | 2026-02-21 | Delayed | 8 | 796 | 5 | 801 | Yes | contact104@mail.com | 9646042247 | 5
P139 | Quantum Labs | CANADA | E-commerce | Referral | Web Development | 5000 | 22000 | USD | 2026-01-22 | 2026-02-14 | 2026-02-21 | Completed | 3 | 507 | 60 | 567 | Yes | contact158@mail.com | Not Provided | 1
P140 | Pixel Agency | CANADA | FinTech | Website | Web Development | 8000 | 9000 | USD | 2026-01-09 | 2026-01-21 | 2026-01-28 | Completed | 4 | 221 | 5 | 226 | No | contact97@mail.com | 9422225701 | 5
P141 | Beta Solutions | AUSTRALIA | SaaS | Website | SEO | 12000 | 18000 | USD | 2026-01-29 | 2026-03-14 | 2026-03-14 | In Progress | 4 | 754 | 20 | 774 | No | contact160@mail.com | Not Provided | 1
P142 | Vertex Global | USA | E-commerce | LinkedIn | SEO | 12000 | 18000 | USD | 2026-01-11 | 2026-02-03 | 2026-02-10 | Completed | 3 | 491 | 5 | 496 | Yes | contact166@mail.com | Not Provided | 3
P143 | AlphaTech | USA | FinTech | Website | App Development | 12000 | 15000 | USD | 2026-01-20 | 2026-01-20 | 2026-01-27 | Completed | 4 | 744 | 0 | 744 | No | contact148@mail.com | Not Provided | 2
P144 | Pixel Agency | INDIA | FinTech | Google Ads | Web Development | 20000 | 12000 | USD | 2026-01-08 | 2026-02-19 | 2026-02-27 | In Progress | 6 | 334 | 10 | 344 | Yes | contact124@mail com | 9531915427 | 5
P145 | Vertex Global | USA | E-commerce | Website | Web Development | 20000 | 22000 | USD | 2026-01-02 | 2026-01-31 | 2026-02-21 | Delayed | 5 | 344 | 0 | 344 | No | contact167@mail.com | Not Provided | 4
P146 | Beta Solutions | UK | Fintech | LinkedIn | UI/UX Design | 12000 | 9000 | USD | 2026-01-05 | 2026-02-18 | 2026-02-18 | Delayed | 6 | 642 | 60 | 702 | No | contact161@mail.com | Not Provided | 3
P147 | Gamma Ltd | USA | E-commerce | Referral | Web Development | 20000 | 25000 | USD | 2026-01-05 | 2026-02-12 | 2026-02-13 | Completed | 8 | 415 | 0 | 415 | No | contact119@mail.com | 9233834123 | 3
P148 | Pixel Agency | AUSTRALIA | FinTech | Referral | SEO | 12000 | 18000 | USD | 2026-01-01 | 2026-03-01 | 2026-03-05 | In Progress | 5 | 440 | 5 | 445 | No | contact125@mail.com | 9909610067 | 3
P149 | Beta Solutions | UK | EdTech | Google Ads | SEO | 12000 | 22000 | USD | 2026-01-21 | 2026-03-10 | 2026-03-15 | In Progress | 6 | 220 | 40 | 260 | No | contact162@mail.com | Not Provided | 3
P150 | Beta Solutions | USA | Fintech | Website | UI/UX Design | 12000 | 22000 | USD | 2026-01-16 | 2026-03-04 | 2026-03-11 | In Progress | 4 | 346 | 5 | 351 | Yes | contact163@mail.com | Not Provided | 2
P151 | Pixel Agency | USA | EdTech | Website | SEO | 15000 | 18000 | USD | 2026-01-19 | 2026-01-29 | 2026-02-01 | Completed | 3 | 240 | 10 | 250 | yes | contact141@mail.com | Not Provided | 5
P152 | Delta Corp | UK | E-commerce | Google Ads | UI/UX Design | 12000 | 12000 | USD | 2026-01-19 | 2026-01-26 | 2026-01-28 | Completed | 2 | 242 | 5 | 247 | No | contact139@mail.com | 9911751370 | 3
P153 | Pixel Agency | USA | Healthcare | LinkedIn | SEO | 15000 | 18000 | USD | 2026-01-22 | 2026-01-29 | 2026-02-04 | Completed | 5 | 472 | 12 | 484 | no | contact147@mail.com | Not Provided | 4
P154 | Gamma Ltd | CANADA | E-commerce | Google Ads | Web Development | 5000 | 18000 | USD | 2026-01-08 | 2026-01-15 | 2026-01-18 | Completed | 4 | 468 | 10 | 478 | Yes | contact129@mail.com | 9908988819 | 2
P155 | Gamma Ltd | USA | SaaS | Website | UI/UX Design | 20000 | 18000 | USD | 2026-01-10 | 2026-01-17 | 2026-01-19 | Completed | 6 | 680 | 20 | 700 | No | contact137@mail.com | 9989351605 | 1
P156 | ZetaSoft | USA | E-commerce | Referral | App Development | 5000 | 9000 | USD | 2026-02-20 | 2026-03-10 | 2026-03-12 | In Progress | 3 | 400 | 9 | 409 | No | contact116@mail.com | 9050654052 | 3
P157 | ZetaSoft | AUSTRALIA | SaaS | Referral | App Development | 12000 | 12000 | USD | 2026-01-30 | 2026-02-10 | 2026-02-15 | Completed | 6 | 374 | 20 | 394 | Yes | contact120@mail.com | 9447765474 | 2
P158 | ZetaSoft | INDIA | FinTech | LinkedIn | Web Development | 15000 | 20000 | USD | 2026-02-12 | 2026-02-27 | 2026-03-04 | In Progress | 7 | 650 | 15 | 665 | No | contact127@mail.com | 9092883061 | 4
P159 | ZetaSoft | INDIA | EdTech | Website | SEO | 5000 | 22000 | USD | 2026-03-08 | 2026-03-20 | 2026-03-25 | In Progress | 8 | 290 | 30 | 320 | Yes | contact133@mail.com | 9025225699 | 5
P160 | ZetaSoft | UK | SaaS | LinkedIn | UI/UX Design | 12000 | 18000 | USD | 20-01-206 | 2026-02-20 | 2026-02-24 | Completed | 5 | 820 | 22 | 842 | No | contact138@mail.com | 9856406373 | 1
P161 | ZetaSoft | USA | EdTech | Referral | App Development | 12000 | 9000 | USD | 2026-02-05 | 2026-02-10 | 2026-02-15 | Completed | 6 | 100 | 43 | 143 | Yes | contact149@mail.com | 9776590306 | 3
P162 | Nova Systems | UK | FinTech | LinkedIn | App Development | 12000 | 18000 | USD | 2026-01-03 | 2026-01-10 | 2026-01-12 | Completed | 8 | 802 | 16 | 818 | No | contact93@mail.com | 9320372535 | 2
P163 | Nova Systems | AUSTRALIA | FinTech | Google Ads | App Development | 15000 | 18000 | USD | 2026-01-10 | 2026-01-17 | 2026-01-19 | Completed | 8 | 24 | 80 | 104 | No | contact94@mail.com | 9390930964 | 3
P164 | Nova Systems | AUSTRALIA | EdTech | Website | UI/UX Design | 15000 | 18000 | USD | 2026-01-13 | 2026-01-20 | 2026-01-22 | Completed | 6 | 246 | 24 | 270 | Yes | contact106@mail.com | 9508105242 | 5
P165 | Nova Systems | USA | FinTech | Google Ads | Web Development | 12000 | 18000 | USD | 2026-01-22 | 2026-01-29 | 2026-02-01 | Completed | 5 | 468 | 32 | 500 | Yes | contact123@mail.com | 9219457946 | 1
P166 | Nova Systems | CANADA | E-commerce | Website | App Development | 20000 | 18000 | USD | 2026-01-24 | 2026-02-01 | 2026-02-03 | Completed | 4 | 680 | 12 | 692 | No | contact132@mail.com | Not Provided | 4